## Sheet1
Assignment | Date | Meeting Date | Activity | Status | Expected Completion | Comments
Project Start | 2019-10-07 | 2019-10-01 | Begin project | In-progress | 2019-12-04
Requirements Research | 10/7 - 10/15 | 10/7, 10/14 | Research Etsy, identify areas of improvement, lay foundations of SOW-type document |  | 2019-10-15
Preliminary Desgin | 10/21 - 10/31 | 10/23, 10/30 | Begin initial production of software. Outline necessities within design |  | 2019-10-31
Data Design | 11/1 - 11/8 | 2019-11-04 | Establish database and provide access to and from through design |  | 2019-11-08
Module Development | 11/11 - 11/20 | 11/11, 11/17 | Apply improvements and implement features |  | 2019-11-20
Testing | 11/20 - 11/22 | 2019-11-21 | Debug and test for quality assurance |  | 2019-11-22
Integration | 11/25 - 12/1 | 2019-11-25 | live case tests |  | 2019-12-01
Final Touches | 12/1 - 12/4 | 12/1, 12/3 | Implement last second changes or improvements. Prepare presentation |  | 2019-12-04
Final Delivery | 2019-12-05 | 2019-12-05 | Final Devlierable delivered |  | 2019-12-06